## CSP Wave 4-Apigee 4.0 migration
Special: | [7 empty] | DEVTST | 0.1-.3,
Arg Holiday --> |  |  |  | .5, | .1, .2 |  |  |  | PROD | [6 empty] | .4,
PRC Holiday -->
US Holiday --> | [12 empty] | .1,
|  | March |  |  |  | April |  |  |  | May |  |  |  |  | June
| 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Wave 4 Activities
Apigee to push Wave 4 apigee changes for all services in QA - Apigee 3.8 |  |  |  |  | 0.1-0.5 | 0.1-0.2
Anand and Apigee to validate Wave 4 changes for all services for QA- Apigee 3.8 |  |  |  |  | 0.3 | 0.3 | [6 empty] | LEGEND
Existing Apigee 3.8 changes for Wave 4 code for QA ENV (Test by each service) |  |  |  |  | 0.3-0.4 | 0.4-0.5 | [7 empty] | Apigee responsible
Apigee to push Wave 4 apigee changes for all services in QA - Apigee 3.8 |  |  |  |  | 0.1-0.2 | 0.1-0.2 | [7 empty] | IDT and datacenter related
Anand and Apigee to validate Wave 4 changes for all services for QA- Apigee 3.8 |  |  |  |  | 0.3 | 0.3 | [7 empty] | Production weeks
Existing Apigee 3.8 changes for Wave 4 code for Stress ENV (Test by each service) |  |  |  |  | 0.4-0.5 | 0.4-0.5 | [7 empty] | Go live times
Wave 4 code- Stress Test (WW15.1-16.5) (Apigee 3.8) | [5 empty] | IDT uses ENV | Available for non-IDT services from 10AM PST-3 AM PST | [6 empty] | Program milestones
Wave 4 Identity Requirement for Release activities - Wave 4 |  |  |  | 0.2 | [9 empty] | Holiday schedule
Apigee to push Wave 4 apigee changes for all services in DEVTST - Apigee 3.8 | [7 empty] | 0.1 | 0.1-0.2
Anand and Apigee to validate Wave 4 changes for all services for DEVTST- Apigee 3.8 | [7 empty] | 0.2 | 0.4
Apigee to push Wave 4 apigee changes for all services in PRD - Apigee 3.8 | [8 empty] | 0.1-0.2
Anand and Apigee to validate Wave 4 changes for all services for PRD- Apigee 3.8 | [8 empty] | 0.4
IDT and DataCenters |  |  |  | - FM + Apigee - AWS (without Apigee) | - FM + Apigee - AWS (without Apigee) | AWS + FM + Apigee + couchbase | AWS + FM + Apigee + couchbase | AWS + FM + Apigee + couchbase | AWS + FM + Apigee + couchbase | AWS + FM + Apigee + couchbase | AWS + FM + Apigee + couchbase
DEVTST readiness for all services | [6 empty] | 0.1-0.4
DEVTST Deployments for all services | [6 empty] | 0.3-0.5 | 0.1-0.2
Code Freeze | [6 empty] | 16.3/16.5
Complete E2E Integration of all services will be in DEVTST | [7 empty] | 0.2-0.5
PROD push for all services | [8 empty] | 0.1-0.5
## Apigee 4.0 migration schedule below ##
Infrastructure setup needed for Apigee 4.0 migration
Spin up new web servers for services that don’t manage datacenters config in their DB | [5 empty] | 0.3
New CNAME for all new web servers | [5 empty] | 0.3
Generate new client id and secrets for all services that use new web servers | [5 empty] | 0.4-0.5
Service teams to make sure New ENV works as expected [By service] | [6 empty] | 0.1-0.5 | 0.1-0.5
Make configuration changes for the services to point to Apigee 4.0 endpoints for dependent services for new web servers [Done by service team] + DNS Cut over etc + Review Visio changes with each service team | [5 empty] | 0.3-0.5 |  |  | 0.3-0.5
Apigee to do target endpoint changes for go live
1. What if upgrade doesn’t go over well. What is the rollback plan ? 2. Web server spin up and spin down 3. Configuration changes that need to happen before and after upgrade 4. CNAME changes before and after 5. Failover scenarios with the parallel ENV approach by each service 6. Having someone on standby from IT to support us during go live time etc. 7. I am sure I am missing a few things. Once you guys can provide this, we can add this to this schedule.
INT ENV (Pre-Prod)
Apigee 4.0 upgrade in INT (Test by each service)(Wave3) |  |  |  | 0.3 | 0.1-0.5
Apigee to push Wave 3 bundle into QA, Stress, DEVTST, PRD | [5 empty] | 0.1-0.5
Apigee to push Wave 4 apigee changes for all services in INT |  |  |  |  | 0.1-0.2 |  |  |  | 0.1-0.5
Anand and Apigee to validate Wave 4 changes for all services for INT |  |  |  |  | 0.3 |  |  |  | 0.5
Services to push Wave 4 code into INT | [8 empty] | 0.4-0.5
E2E Integration test with all Wave 4 services in INT ENV and Apigee 4.0 | [6 empty] | 0.1-0.3 |  |  | 0.1-0.5
QA ENV (Pre-Prod)
Apigee to push Wave 4 apigee changes for all services in QA | [5 empty] | 0.1-0.2 |  | 0.4-0.5 |  |  | 0.1-0.2
Anand and Apigee to validate Wave 4 changes for all services for QA | [5 empty] | 0.3 |  | 0.5 |  |  | 0.2
Services to push Wave 4 code into QA (new Web server) | [6 empty] | 0.4-0.5 |  |  |  | 0.3
Apigee 4.0 upgrade in QA (Test by each service) | [7 empty] | 0.1-0.5 |  |  |  | 0.1-0.5
Apigee 4.0 Pre-PROD Go live (QA and INT) | [12 empty] | 0.1
Buffer for any issues in Pre-PROD after go live (QA and INT) | [8 empty] | 0.1-0.3 |  |  |  | 0.2
Stress Activities
Apigee Performance Test (Run by apigee) - Wave 3 and 4.0 |  |  |  | .3,.4,.5 | 0.4-0.5
Apigee gives 4.0 stress ENV to Intel- Wave 3 |  |  |  |  | 0.5
Apigee to push Wave 4 apigee changes for all services in Stress | [5 empty] | 0.1-0.2 |  |  |  |  | 0.3-0.4
Anand and Apigee to validate Wave 4 changes for all services for Stress | [5 empty] | 0.3 |  |  |  |  | 0.5
Services to push Wave 4 code into Stress | [10 empty] | 0.4-0.5
Apigee 4.0 upgrade in Stress (Test by each service) | [11 empty] | 0.1-0.5
Intel Wave 4 and Apigee 4.0- performance Test (Christmas test) | [12 empty] | 0.4
Apigee 4.0 Stress ENV Go live | [12 empty] | 0.3
Buffer for any issues in Stress after go live | [12 empty] | 0.4
Apigee Performance Test (Run by apigee) - Wave 4 and 4.0 | [11 empty] | 0.4-0.5 | 0.5
DEVTST
Apigee to push Wave 4 apigee changes for all services in DEVTST | [7 empty] | 0.1-0.2 |  |  |  |  | 0.1-0.3
Anand and Apigee to validate Wave 4 changes for all services for DEVTST | [7 empty] | 0.3 |  |  |  |  | 0.4-0.5
Services to push Wave 4 code into DEVTST (new Web server) | [8 empty] | 0.1-0.4 |  |  | 0.4-0.5
Apigee 4.0 upgrade in DEVTST (Test by each service) + Data migration validation | [12 empty] | 0.1-0.4 | 0.1-0.5
Apigee 4.0 Go live- DEVTST | [10 empty] | 0.1 |  |  |  | 0.1
Buffer for any issues in DEVTST after go live- DEVTST | [10 empty] | 0.2-0.3 |  |  |  | 0.2-0.3
PROD
Apigee to push Wave 4 apigee changes for all services in PRD | [8 empty] | 0.1-0.2 |  |  |  | 0.1-0.3
Anand and Apigee to validate Wave 4 changes for all services for PRD | [8 empty] | 0.3 |  |  |  | 0.4-0.5
Services to push Wave 4 code into PRD (new Web server) | [12 empty] | 0.1-0.2
Apigee 4.0 upgrade in PRD (Test by each service) + Data migration validation | [12 empty] | 0.3-0.5 | 0.1-0.5
Apigee 4.0 Go live- PRD | [10 empty] | 0.3 |  |  |  | 0.3
Buffer for any issues in PRD after go live- PRD | [10 empty] | 0.4-0.5 |  |  |  | 0.4-0.5
Program Go live dates |  |  |  |  | Feature complete |  | Comm Go live; 0.5: Code Freeze | Wave 4 DEVTST | Wave 4 PRD | INT/QA and Stress apigee 4.0 | DEVTST and PRD apigee 4.0 |  | INT/QA and Stress apigee 4.0 |  | DEVTST and PRD apigee 4.0
Assumptions
DB needs to be restored before 10 AM PST after IDT finished their tests
Rodolfo to work with Ricardo and Sridhar and stop replication between AWS and FM so AWS can be used by itself for IDT team for stress testing (WW13.1)
Note on F8: Focus on Commerce and identifty by WW14 Deploy end of the week in both QA and Stress
Note on G10: Rest of the QA team start testing by 15.03
Note on E15: Abruzzini, Maria Paula: Performance without Apigee on EG
Note on F15: Abruzzini, Maria Paula: Performance without Apigee on EG
Note on G15: Abruzzini, Maria Paula: Couchbase test on 2 Data Centers
Note on H15: Abruzzini, Maria Paula: Identity Performance Cycle usign Apigee From 4AM PST to 10AM PST
Note on I22: Sathyan, Srinivas: IT needs time to deploy in DEVTST
Note on J25: Sathyan, Srinivas: IDT to go first
Note on G29: ssathya1: Mark to confirm
Note on G30: ssathya1: IT to confirm
Note on H32: ssathya1: Srini and Anand to confirm with service teams
Note on I32: ssathya1: srini and Anand to confirm with service teams
Note on H41: Sathyan, Srinivas: IDT goes first; This will be FC code; Validate INT ENV and apigee 4.0 this code doesn’t have to be bug free from wave 4 perspective; Srini to confirm with Intel teams
Note on J41: Sathyan, Srinivas: IDT goes first; This will be FC code; Validate INT ENV and apigee 4.0
Note on L44: PLAN for Data Migration for Integration and QA
Note on F51: Abruzzini, Maria Paula: We could use Stress (second DataCenter in AWS). We need to validate which configuration is required. Identity will be using Stress (EG data center) without Apigee for Performance Test
Note on L53: DATA Migration for Stress

## Sheet3
Risks | Mitigation
Each environment on APIGEE side has two paths. E.g. Production will have 2 paths – one which goes live and second one which is currently used for testing before pushing it live. We have not done this parallel path to production setup before and hence we don’t have clear picture on how this path would work with Intel environments. | Spin up the ENV early and have service teams test this parallel path out. Srini to confirm
2. Since the database is common for all Intel services, even if we spin up a new webserver with different CNAMEs, there is a risk of
a. Invalid/Test Data that requires clean up in future – this might not be easy in some cases. | Teams need to use convention that Srini sent out for test apps and test IDT users; QA teams to clean up the data that they add.
3. At CSP level, we need to define this parallel path (with network diagram), so each team understand the purpose and flow. We don’t want team to use this env. in such a way that it breaks own or other services. | Anand to have a call with all the service teams and communicate to them what the parallel path is and how to use the ENV for testing purposes.
4. As CSP level, we need to define the process very clearly – this should include, development, testing, bug fixing etc. strategy for existing bugs or incidents in PRD or DEVSTST | Anand to have a call with all the service teams and communicate to them what the parallel path is and how to use the ENV for debugging/incident purposes.
DNS Cutover- We need to do this twice instead of one | Mark and team to create a check list for the entire cut over process
Data validation after migration is done in DEVTST and PRD | QA team will be testing this after migration is done
We still have not tested the Real PRD/DEVTST ENV [part of cut over] | We are testing the exact copy of the service team’s code in an alternate ENV; the DB is same as well;
Certificates may not work when switching ENV [part of cut over] | Test and validate certificates after cut over; joint effort between Apigee and Intel; Make sure a call from Apigee is pointing to the correct end point. QA team will test this.